## Sheet1
WORK BREAKDOWN STRUCTURE DICTIONARY
Level | Code | Name | Description | Start Date | End Date | Duration | Assigned to | Deliverables
1 | 1 | Initiation | Iniate the project | 2017-01-16 | 2017-01-31 | 12 days | Hannah Reyes Kyle Lee
2 | 1.1 | Create Project Schedule | Create the schedule of the project | 2017-01-16 | 2017-01-19 | 4 days | Hannah Reyes | Project Schedule
3 | 1.1.1 | Check Time Availability | Know and list time availability of team members | 2017-01-16 | 2017-01-16 | 1 day | Hannah Reyes | Time Availabilty of Team
3 | 1.1.2 | Estimate Project Duration | Give an estimation of the duration of the project | 2017-01-17 | 2017-01-17 | 1 day | Hannah Reyes | Days of Project Duration
3 | 1.1.3 | Know Project Deadline | Know and consider deadlines of the project | 2017-01-18 | 2017-01-18 17:00 | 1 day | Kyle Lee | Project Deadline
3 | 1.1.4 | Create List of Tasks | Create list of things that needs to be done and assign to members | 2017-01-19 08:00 | 2017-01-19 17:00 | 1 day | Hannah Reyes | List of Tasks
2 | 1.2 | Create Project Plan | Create the plan for the project | 2017-01-20 08:00 | 2017-01-24 17:00 | 3 days | Hannah Reyes Kyle Lee | Project Plan
3 | 1.2.1 | Lay-out Project Plan | Make an initial project plan | 2017-01-20 08:00 | 2017-01-20 17:00 | 1 day | Hannah Reyes | Project Plan
3 | 1.2.2 | Update Project Plan | Update the project plan if there is any revision needed | 2017-01-23 08:00 | 2017-01-23 17:00 | 1 day | Kyle Lee | Project Plan
3 | 1.2.3 | Project Checklist | Create a checklist of deliverables to keep track of the project | 2017-01-24 08:00 | 2017-01-24 17:00 | 1 day | Hannah Reyes | Project Checklist
2 | 1.3 | Propose Project | Propose the project to client/professor | 2017-01-25 08:00 | 2017-01-25 17:00 | 1 day | Hannah Reyes | Project Concept
3 | 1.3.1 | Create Project Proposal | Create the document to be passed for the project proposal | 2017-01-25 08:00 | 2017-01-25 17:00 | 1 day | Hannah Reyes | Project Proposal
2 | 1.4 | Track Project | Track the progress of the project | 2017-01-26 08:00 | 2017-01-31 17:00 | 4 days | Kyle Lee | Project
3 | 1.4.1 | Create Progress Reports | Create reports that indicates the progress of the project | 2017-01-26 08:00 | 2017-01-26 17:00 | 1 day | Hannah Reyes | Progress Report
3 | 1.4.2 | Analyze Project Performance | Analyze the performace of the project so far | 2017-01-27 08:00 | 2017-01-31 17:00 | 3 days | Hannah Reyes | Project Performance
1 | 2 | Planning | Creating of a set of plans to help guide the team | 2017-02-01 08:00 | 2017-02-27 17:00 | 19 days | Hannah Reyes Kyle Lee
2 | 2.1 | Prepare Needed Documents | Create the needed documents for the project | 2017-02-01 08:00 | 2017-02-09 17:00 | 7 days | Hannah Reyes | Documents
3 | 2.1.1 | Work Breakdown Structure | Create the work breakdown structure of the project | 2017-02-01 08:00 | 2017-02-01 17:00 | 1 day | Kyle Lee | WBS
3 | 2.1.2 | Project Schedule | Create Project Schedule | 2017-02-02 08:00 | 2017-02-03 17:00 | 2 days | Hannah Reyes | Project Schedule
3 | 2.1.3 | Communication Plan | Create Communication Plan | 2017-02-03 08:00 | 2017-02-06 17:00 | 2 days | Hannah Reyes Kyle Lee | Communication Plan
3 | 2.1.4 | Quality Plan | Create Quality Plan | 2017-02-04 08:00 | 2017-02-07 17:00 | 2 days | Hannah Reyes Kyle Lee | Quality Plan
3 | 2.1.5 | Procurement Plan | Create Procurement Plan | 2017-02-05 08:00 | 2017-02-07 17:00 | 2 days | Hannah Reyes Kyle Lee | Procurement Plan
3 | 2.1.6 | Project Plan | Create Project Plan | 2017-02-06 08:00 | 2017-02-08 17:00 | 3 days | Hannah Reyes Kyle Lee | Project Plan
3 | 2.1.7 | Budget Planning | Create Budget Plan | 2017-02-07 08:00 | 2017-02-09 17:00 | 3 days | Hannah Reyes Kyle Lee | Budget Plan
2 | 2.2 | Create Preliminary Design | Create project's initial design | 2017-02-10 08:00 | 2017-02-17 17:00 | 6 days | Kyle Lee | Design
3 | 2.2.1 | Develop Project Architecture | Commence development of the project architecture | 2017-02-10 08:00 | 2017-02-14 17:00 | 3 days | Kyle Lee | Project Architecture
3 | 2.2.2 | Prepare ERD | Create Entity Relationship Diagram | 2017-02-15 08:00 | 2017-02-15 17:00 | 1 day | Kyle Lee | ERD
3 | 2.2.3 | Prepare DFD | Create Data Flow Diagram | 2017-02-16 08:00 | 2017-02-16 17:00 | 1 day | Kyle Lee | DFD
3 | 2.2.4 | Prepare Activity Diagram | Create Activity Diagram | 2017-02-17 08:00 | 2017-02-17 17:00 | 1 day | Kyle Lee | Activity Diagram
2 | 2.3 | Create Detailed Design | Enhance project design | 2017-02-20 08:00 | 2017-02-20 17:00 | 1 day | Kyle Lee | Design
3 | 2.3.1 | Create Data Dictionary | Create Data Dictionary | 2017-02-20 08:00 | 2017-02-20 17:00 | 1 day | Kyle Lee | Data Dictionary
2 | 2.4 | Document Design | Design the created documents | 2017-02-21 08:00 | 2017-02-22 17:00 | 2 days | Hannah Reyes | Design
3 | 2.4.1 | Develop Design Specifications | Create the specifications of the design | 2017-02-21 08:00 | 2017-02-22 17:00 | 2 days | Kyle Lee | Design Specifications
2 | 2.5 | Review Design | Review created designs | 2017-02-23 08:00 | 2017-02-27 17:00 | 3 days | Hannah Reyes | Design
3 | 2.5.1 | Review Developed Design | Review the developed designs | 2017-02-23 08:00 | 2017-02-27 17:00 | 3 days | Hannah Reyes | Design
1 | 3 | Execution | Build the physical project deliverables | 2017-02-28 08:00 | 2017-04-13 17:00 | 33 days | Hannah Reyes Kyle Lee
2 | 3.1 | Verify & Validate User Requirements | Verify that the created deliverables meets the user requirements | 2017-02-28 08:00 | 2017-04-06 17:00 | 28 days | Hannah Reyes | User Requirements
3 | 3.1.1 | Design System | Create the design for the system | 2017-02-28 08:00 | 2017-03-03 17:00 | 4 days | Kyle Lee | System Design
3 | 3.1.2 | Develop Software | Commence development of the application/project | 2017-02-28 08:00 | 2017-04-06 17:00 | 28 days | Hannah Reyes Kyle Lee | Software Develop
2 | 3.2 | Integration & Testing | Test developed prototype | 2017-04-07 08:00 | 2017-04-10 17:00 | 2 days | Hannah Reyes | Test Results
3 | 3.2.1 | Complete Integrated Project Plan | Finish the integrated project plan | 2017-04-07 08:00 | 2017-04-07 17:00 | 1 day | Hannah Reyes | Integrated Project Plan
3 | 3.2.2 | Test Analysis Report | Analyze the project testing | 2017-04-08 08:00 | 2017-04-10 17:00 | 1 day | Hannah Reyes | Test Analysis Report
2 | 3.3 | Perform Development Testing | Start testing for development | 2017-04-11 08:00 | 2017-04-13 17:00 | 3 days | Hannah Reyes | Development Results
3 | 3.3.1 | Iterate Project | Iterate the project if needed | 2017-04-11 08:00 | 2017-04-13 17:00 | 3 days | Hannah Reyes | Project
1 | 4 | Control | Documenting the new process, training and creating a plan to monitor the process | 2017-04-14 08:00 | 2017-04-18 17:00 | 3 days | Hannah Reyes Kyle Lee
2 | 4.1 | Project Implementation | Implement the created project | 2017-04-14 08:00 | 2017-04-17 17:00 | 2 days | Hannah Reyes Kyle Lee | Project Implementation
3 | 4.1.1 | Project Execution | Execute the project | 2017-04-14 08:00 | 2017-04-14 17:00 | 1 day | Hannah Reyes Kyle Lee | Project Execution result
3 | 4.1.2 | User Acceptance | Gather feedback from users | 2017-04-14 08:00 | 2017-04-14 17:00 | 1 day | Kyle Lee | User Feedback
3 | 4.1.3 | Implement Approved Training Plan | Create a plan for training | 2017-04-14 08:00 | 2017-04-17 17:00 | 2 days | Hannah Reyes | Training Plan
2 | 4.2 | Conduct Closeout Task | Prepare for project closeout | 2017-04-18 08:00 | 2017-04-18 17:00 | 1 day | Hannah Reyes | Closeout Task
3 | 4.2.1 | Project Transition Checklist | Create a checklist for the transition of the project | 2017-04-18 08:00 | 2017-04-18 17:00 | 1 day | Hannah Reyes | Transition Checklist
1 | 5 | Close Out | Finalizes all project activities completed across all phases | 2017-04-19 08:00 | 2017-04-26 17:00 | 6 days | Hannah Reyes Kyle Lee
2 | 5.1 | Operations & Maintenance | Perform operations and project maintenance | 2017-04-19 08:00 | 2017-04-26 17:00 | 6 days | Hannah Reyes | Operations & Maintenance
3 | 5.1.1 | Document Lessons Learned | Figure out lessons learned and document them | 2017-04-19 08:00 | 2017-04-19 17:00 | 1 day | Hannah Reyes Kyle Lee | Lessons Learned
3 | 5.1.2 | Update Files/Records | Update all files that needs to be updated | 2017-04-20 08:00 | 2017-04-21 17:00 | 2 days | Hannah Reyes | Updated Files
3 | 5.1.3 | Archive Files/Documents | Archive all files for documentation | 2017-04-21 08:00 | 2017-04-24 17:00 | 2 days | Kyle Lee | Archived Files
3 | 5.1.4 | Post Implementation Review | Create a review after the implementation of the project | 2017-04-22 08:00 | 2017-04-26 17:00 | 3 days | Hannah Reyes | Implementation Review
3 | 5.1.5 | Performance Measure | Measure the performance of the project after its implementation | 2017-04-23 08:00 | 2017-04-26 17:00 | 3 days | Hannah Reyes | Performance Result